## Slide 1: Budget, Schedule, Management
Marco Oriunno, July 11, 2013
HPS DOE Review

## Slide 2: Outline
Organization
Schedule
Costs
Manpower
Risk Management
Project Monitoring

## Slide 3: Organization Chart
DOE HEP
JLAB
SLAC
Heavy Photon Search Project Manager M. Oriunno Project Scientists J. Jaros (SLAC) S. Stepanyan (JLAB)
HPS Executive Committee
Beamline (K.Moffeit)
SVT (T.Nelson)
Ecal (R.Dupre)
SVT DAQ (R.Herbst)
Trigger/DAQ (S.Boyarinov)
Muon (K.Griffioen)
Slow Controls (H. Egiyan)
Software (M.Haltrop)
Analysis (M.Graham)
HPS Project
INFN
IPNO
Funding Agencies
The Project Scientists hold the budget at SLAC and JLAB
The Project Manager holds the contingencies
DOE NP

## Slide 4: Matrix of Deliverables
 | SLAC | UCSC | JLAB | ORSAY | INFN
Beamline | ● |  | ● |  | 
SVT | ● | ● |  |  | 
SVT DAQ | ● | ● |  |  | 
ECAL |  |  | ● | ● | ●
TDAQ | ● |  | ● | ● | 
Slow Control |  |  | ● |  | 
Installation & Commissioning | ● | ● | ● | ● | ●
Project management | ● |  | ● |  | 

## Slide 5: Work Breakdown Structure (WBS)
WBS | NAME
1.1 | Beamline
1.2 | SVT
1.3 | SVT DAQ
1.4 | ECAL
1.5 | TDAQ
1.6 | Slow Control
1.7 | Installation & Commissioning
1.8 | Electron running
1.9 | SLAC Travel and Meetings
1.10 | SLAC Travel for Data Run
1.11 | Project management
1.12 | UCSC (pass through)
Construction
Operations
Operations
Construction

## Slide 6: Schedule Drivers – Staging Plan
HPS Construction
Data Runs
Analysis
Mar.13
Oct.’14
May.’15
Sep.’16
Early Physics Window Opportunity
FY13
FY15
FY16
FY14
Construction
Operations
Funding
Construction
Testing
I&C
Stage 1
Stage 2
Stage 3
Stage 4
Installation & Commissioning
Data Run
Analysis

## Slide 7: Schedule Drivers – Endgame Milestones
HPS Construction
Data Runs
Analysis
Mar.13
Oct.’14
May.’15
Sep.’16
Early Physics Window Opportunity
FY13
FY15
FY16
FY14
Construction
Operations
End Milestone 1
End Milestone 2
End Construction: “Installation and the commissioning of HPS on the beamline, no beam”. September 30 ’14
End of Data Runs : Data Runs at 1.1, 2.2 and 6.6 GeV. March 31’15
Funding

## Slide 8: HPS Master Schedule – Staging Plan
Early Physics Window Opportunity
Beamline
SVT
SVT DAQ
ECAL
TDAQ
SLOW Control
Installation and Comm.
Data Run
Construction
Testing
Installation
Stage 1
Stage 2
Stage 3
Data Run
Stage 4

## Slide 9: Schedule – Beamline (HPS downstream in the Alcove)
Milestones & Reviews
Beamline Design review 12 - Dec -2013
Installation review 18 - Aug - 2014
Beamline Installed 26 – Sep - 2014
Vacuum Box and Target works can start at SLAC > Jan. 2014
Work at JLAB can start only > March 2014 (Driven by Manpower Availability)

## Slide 10: Schedule – SVT Mechanics
Milestones&Reviews
SVT+DAQ Engineering Design Review 20 – Aug- 2013
Layer 1-3 Ready 17 – Feb - 2014
Layer 4-6 Ready 18 – Feb - 2014
SVT Ready for Shipment (Tested with DAQ) 9 - June - 2014
SVT + DAQ Ready For Installation 15 – Aug - 2014
Work C-Supports, Baseplate…can start only > Oct’13
(Driven by Manpower Availability, not on the Critical Path)

## Slide 11: Schedule – SVT DAQ
Milestones&Reviews
Eng. Review (Combined SVT) 20-Aug-2013
FE board tested w/ hybrid 28-Aug-13
Flange DAQ Electrically tested 10-Jan-14
DAQ full system Test 2-Jun-14
Start FY14, Driven by Funds availability
Start FY14, Driven by Funds availability
FE Boards
Hybrids
Flange Boards
DAQ
Flex Cables

## Slide 12: Schedule – SVT + DAQ Integration

## Slide 13: Schedule – ECAL
Milestones&Reviews
Motherboard Shipped at JLAB 10-Feb-14
Preamplifiers Shipped at JLAB 4-Apr-14
ECAL Ready for installation 1-Aug-14

## Slide 14: Schedule –TDAQ , Slow Control
TDAQ ready Dec.6, 2013 (Integration in the existing TDAQ of the Hall-B)
Slow Control Starts Aug’13 Ready Aug.8, 2014

## Slide 15: Schedule - Software
Milestones&Reviews
Reconstruction Ready 19-Feb-14
Ready to Run 5-Mar-14

## Slide 16: Schedule – Installation, Commissioning and Data Runs
Installation in Hall-B ~2 wk at the end of August, done by the same crew of the Test Run
Commissioning and Data Run | Duration | Start | End
Beamline Commissioning (2014) | 1 wk | 29-Sep | 3-Oct
Detector Commissioning Run (2014) | 2 wks | 6-Oct | 17-Oct
Data Run 2.2GeV (2014) | 2 wks | 20-Oct | 31-Oct
Data Run 1.1 GeV (2014) | 2 wks | 3-Nov | 14-Nov
Beamline recommissioning (2015) | 2 wks | 5-Jan | 16-Jan
Data Run (2015) | 8 wks | 19-Jan | 13-Mar

## Slide 17: Costs Methodology
Schedule and Costs are simultaneously managed with MSProject
Tasks are tracked down to WBS Level 3 Min.
Labor is added in hours by skills. M&S as number of required units
Only Engineering Labor + Overheads (SLAC = 53% , 7.65%, JLAB = 49% , 49%
Inflation 2.5% per year
Contingency :
  10% Catalogue Items
  20-25% Similar to previous design
  30-50% New design
Lab.
M&S

## Slide 18: HPS Total Costs = $3,187k
Chart: 
Chart: 
| SLAC Travel Meetings | SLAC Travel for Comm. and Run. | UCSC Funds (Pass through) | ECAL | Installation & Commissioning | Slow Control | TDAQ | Project management | Beamline | SVT
 | 124.7562 | 155.8611 | 462.9059 | 17.5063 | 57.937 | 133.522 | 161.0552 | 166.8851 | 468.5383 | 656.179
Construction
Operations
k
k
k
k
k
k

## Slide 19: HPS Budget vs. Test Run
Funded in July 2011 for installation in March 2012
First FWP $751k
Additional $200k for missing items, underestimating engineering and technicians
Slow response from external shops, recovered with an increase of Labor in-house
Installation done on April 18, ~ 7 weeks delay
Lesson learned : Better contingency, realistic engineering estimations, better planning of the purchasing process.

## Slide 20: Capital Equipments vs. Operations (*)
Capital Equipment (CE) | Labor and Material costs of the parts constituting the experimental apparatus, which is required to perform the physics. They do not include spares and prototyping
Infrastructures (INFRA) | Labor and Materials cost for general purpose infrastructures required by the apparatus, which can be reused for other experiments, e.g, Chiller, Power Supplies, PLC
Operation (OP) | Labor and Material Costs incurred for the commissioning and the operation of the experimental set up, as well as Spare Parts, Prototype and R&D activities. Travels.
< $2M
 |  | Labor | Material | Total |  | Operations | Infrastractures | Capital Equipments
1 | HPS | $1,930 | $1,257 | $3,187 |  | $928 | $568 | $1,692
1.1 | Beamline | $285 | $184 | $469 |  | $0 | $325 | $143
1.2 | SVT | $452 | $204 | $656 |  | $75 | $43 | $539
1.3 | SVT DAQ | $431 | $352 | $782 |  | $80 | $162 | $540
1.4 | ECAL | $12 | $6 | $18 |  | $0 | $0 | $18
1.5 | TDAQ | $151 | $10 | $161 |  | $0 | $10 | $151
1.6 | Slow Control | $94 | $39 | $134 |  | $0 | $28 | $106
1.7 | Installation & Commissioning | $58 | $0 | $58 |  | $55 | $0 | $3
1.8 | Electron Running | $0 | $0 | $0 |  | $0 | $0 | $0
1.9 | SLAC Travel Meetings | $125 | $0 | $125 |  | $125 | $0 | $0
1.10 | SLAC Travel for Commissioning and Running | $156 | $0 | $156 |  | $130 | $0 | $26
1.11 | Project management | $167 | $0 | $167 |  | $0 | $0 | $167
1.12 | UCSC Funds | $0 | $463 | $463 |  | $463 | $0 | $0
* Thanks to H.Marsiske for the help with DOE Guidelines

## Slide 21: Beamline Costs: Upstream vs. Downstream
Beamline Downstream - ALCOVE | Labor | M&S | Total
Refurbishing of the Alcove | $202 | $118 | $320
Platform in the Alcove | $57 | $53 | $110
Magnet Power | $9 | $26 | $35
Beamline controls | $136 | $39 | $175
Beamline Upstream (Proposal) | Labor | M&S | Total
Items not required in the Alcove | $8 | $65 | $74
Vacuum beam line downstream of chicane | $0 | $19 | $19
Frascati Vacuum Chamber | $0 | $19 | $19
Photon Dump & Shielding | $8 | $27 | $35
Saving $74k =
Increase $320k -
With the recent CEBAF Re-Baselining Review, JLAB management has led the development of a realistic schedule for HPS in Hall B.
HPS can be installed in September, 2014, commissioned in early FY2015, and take data later in FY2015 if it is installed in the Hall B Downstream Alcove instead of the upstream location described in the proposal.
Alcove running is fully compatible with CLAS 12 assembly schedule in Hall B and ideal for future running when CLAS 12 is operational.
Net Incr. $246k
The additional costs to refurbish the Alcove are considered HPS Infrastructures

## Slide 22: Cost Breakdown by participants
SLAC Total=$2.473M
JLAB Total=$714k
JLAB |  | Labor | Material | Total | Capital Equipments
1 | HPS | $530 | $184 | $714 | $360
1.1 | Beamline | $244 | $167 | $411 | $86
1.4 | ECAL | $12 | $6 | $18 | $18
1.5 | TDAQ | $151 | $0 | $151 | $151
1.6 | Slow Control | $94 | $11 | $106 | $106
1.7 | Installation & Commissioning | $29 | $0 | $29 | $0
SLAC |  | Labor | Material | Total | Capital Equipments
1 | HPS | $1,400 | $1,074 | $2,473 | $1,332
1.1 | Beamline | $41 | $17 | $58 | $58
1.2 | SVT | $452 | $204 | $656 | $539
1.3 | SVT DAQ | $431 | $352 | $782 | $540
1.5 | TDAQ | $0 | $10 | $10 | $0
1.6 | Slow Control | $0 | $28 | $28 | $0
1.7 | Installation & Commissioning | $29 | $0 | $29 | $3
1.8 | Electron Running | $0 | $0 | $0 | $0
1.9 | SLAC Travel Meetings | $125 | $0 | $125 | $0
1.10 | SLAC Travel for Commissioning and Running | $156 | $0 | $156 | $26
1.11 | Project management | $167 | $0 | $167 | $167
1.12 | UCSC Funds | $0 | $463 | $463 | $0

## Slide 23: Infrastructures, Total $568k
WBS | Name | Labor | Material | Total
1.1 | Beamline | $211 | $124 | $335
 | Platform in the Alcove | $57 | $53 | $110
 | Magnet Power | $9 | $26 | $35
 | New Beamline El. & Diagnostics | $136 | $39 | $175
 | Beam Offset Monitor | $10 | $6 | $16
1.2 | SVT | $0 | $43 | $43
 | Chiller | $0 | $39 | $39
 | Equipment for chiller Control | $0 | $4 | $4
1.3 | SVT DAQ | $0 | $162 | $162
 | SVT COB | $0 | 54 | $54
 | RTM | $0 | 23 | $23
 | Crates | $0 | 15 | $15
 | SVT LV Unit | $0 | $17 | $17
 | SVT HV Unit | $0 | $37 | $37
 | Wiener Crate | $0 | $16 | $16
1.6 | Slow Control | $0 | $28 | $28
 | PLCs Modules for controls | $0 | $28 | $28

## Slide 24: Additional ECAL Funds - Orsay + INFN, € 223k
IPNO ORSAY, € 128k + € 38k (~30% contingency)
Young Researchers Grant awarded from Agence Nationale de la Recherche (ANR) for HPS. It will be used for new Preamplifiers, part of the LMS, Mechanics, Assembly
€ 34k M&S , € 64k Labor, € 30k Travels ,
Engineering provided as in-kind (ME, EE Design and Installation)
INFN*, € 95k + € 27k (~30% contingency)
Requesting funds to INFN in July for new Motherboards, the Light Monitoring System (€ 70k) and Travel (€ 25k). Decision expected by mid September. High chance to pass. € 40k already secured by INFN carry over funds of the Forward Tagger in Hall-B.
* Cagliari-Catania-Genova-Roma2-Torino

## Slide 25: Spending Profile
Chart: 
| 41365 | 41395 | 41426 | 41456 | 41487 | 41518 | 41548 | 41579 | 41609 | 41640 | 41671 | 41699 | 41730 | 41760 | 41791 | 41821 | 41852 | 41883 | 41913 | 41944 | 41974 | 42005 | 42036 | 42064 | 42095 | 42125 | 42156 | 42186 | 42217 | 42248 | 42278 | 42309 | 42339 | 42370 | 42401 | 42430 | 42461 | 42491 | 42522 | 42552 | 42583
Rate | 10475.72 | 16019.7438 | 113225.0345 | 197178.468 | 99979.0901 | 126528.5984 | 382363.2314 | 373254.7056 | 125427.2726 | 156194.2087 | 124197.7193 | 103800.4057 | 117143.0588 | 86806.2276 | 94755.1154 | 131783.7331 | 77990.0544 | 33903.6218 | 60755.589 | 60852.7182 | 20018.3339 | 57919.1727 | 45806.4687 | 31156.3685 | 18774.0232 | 63154.033 | 18774.0232 | 19627.3924 | 17920.654 | 1920.0714 | 13815.8056 | 14506.5959 | 15888.1764 | 14506.5959 | 14506.5959 | 15888.1764 | 14506.5959 | 37814.0757 | 15197.3862 | 14506.5959 | 12520.5676
Total | 10475.72 | 26495.4638 | 139720.4983 | 336898.9663 | 436878.0564 | 563406.6548 | 945769.8862 | 1319024.5917 | 1444451.8643 | 1600646.073 | 1724843.7924 | 1828644.1981 | 1945787.2569 | 2032593.4845 | 2127348.5999 | 2259132.3331 | 2337122.3874 | 2371026.0092 | 2431781.5982 | 2492634.3164 | 2512652.6503 | 2570571.8231 | 2616378.2918 | 2647534.6603 | 2666308.6835 | 2729462.7165 | 2748236.7397 | 2767864.1321 | 2785784.7862 | 2787704.8576 | 2801520.6632 | 2816027.2591 | 2831915.4355 | 2846422.0314 | 2860928.6273 | 2876816.8037 | 2891323.3996 | 2929137.4752 | 2944334.8614 | 2958841.4573 | 2971362.0249
Keep alive funds FY13
$414k
FY14 - FY15 - FY16
SVT Review
Beamline Review

## Slide 26: Manpower – FTE Labor Breakdown
SLAC
JLAB
 | FY13 | FY14 | FY15 | FY16
ME | 0.19 | 0.64 | 0.14 | 0.02
MD | 0.09 | 0.30 | 0.00 | 0.00
MT | 0.08 | 0.49 | 0.00 | 0.00
EE | 0.58 | 0.76 | 0.05 | 0.02
ET | 0.01 | 0.04 | 0.00 | 0.00
 | FY13 | FY14 | FY15 | FY16
ME# | 0.00 | 0.12 | 0 | 0
MD# | 0.05 | 0.54 | 0 | 0
MT# | 0.00 | 0.66 | 0 | 0
EE | 0.12 | 1.19 | 0 | 0
ET | 0.02 | 0.07 | 0 | 0
Electrical Engineering
Ryan Herbst(EE)*, Ben Reese(EE)
Mechanical Engineering
Marco Oriunno(ME)*, Shawn Osier(ME), Matt McCulloch(MT)*, Matt Swift(MD)
* Participated in the Test Run
Electrical Engineering
Ben Raydo(EE)*, Scott Kaneta(EE)*, Chris Cuevas(EE)*, Nerses Gevorgyan(EE)*, Krister Bruhwel(ET)*
Mechanical Engineering
Hall-B Engineering Team*
# Increase w.r.t. the Proposal, due to the Alcove

## Slide 27: Risk Management
Failure Mode | Consequence | Mitigation
Equipment |  | 
Beam damages silicon or ECAL in electron commissioning | Part or full sub detector not working | Beam Monitors and Interlocks. Spares modules for Layer 1-3
Failure of in-vacuum electronics (hybrid or front end board) | Part or full SVT not working. Need to break vacuum to repaire the failure with a prolonged Beamline shutdown | Extensive testing at SLAC in real conditions and at JLAB before installation. It can be repaired during a short access
Coolant leak in vacuum | Not possible to operate the SVT without cooling. SVT shutdown. Vacuum enviroment Pollution. Beamline shutdown | Minimize number of fittings. Only welded connections. Extensive test at SLAC and JLAB before installation. Pressure check before to close the vacuum chamber. It can be repaired during a short access
Failure to pump down adequately because of excessive SVT outgassing | High beam-gas background. Unable to perform the physics. It may need to break vacuum to repaire the failure with a prolonged Beamline shutdown | Exentsive qualification of the construction materials based on the experience with the Test Run.
CLAS 12 construction mishap breaks beam line vacuum | Hall-B is not able to provide beam to HPS | Careful check of the CLAS12 construction procedures. Mitigation plan shared with CEBAF Hall-B and Clas12.
SVT DAQ - Flange Board. New design, which requires more time than expected. | Schedule Delay and cost overrun | Design work shared woith other SLAC projects. High contingency (50%) in the WBS
Schedule and Budget |  | 
Late Funding beyond FY14 | Schedule delayed till funds available. Risk to miss the early physics window in FY15 | Absorbing delays of the critical task on the contingency carried over from the previous funding period on schedule and budget. Not Critical for Beamline, Ecal, TDAQ.
Partial Funding | Unable to deliver the project in time and with the declared performances. | Need to redefine the size, eventually the scope, of the project
SLAC manpower inadequate to complete SVT DAQ work on schedule | Delays on the SVT DAQ milestones | Current estimation based on what we learned from the Test Run. Same engineering team. WBS Contingency 30%
Ecal support (manpower or funding) inadequate at Orsay/INFN | Delays on the ECAL milestones | ECAL manpower is in-kind. 30% contingency included
Sufficient JLAB Engineering manpower not available for beamline | Delays on the beamline milestones. Inadequate beamline for the HPS phyisics runs. | Current estimation based on what we learned from the Test Run. WBS Contingency 30%. Redifine the schedule and the goals of the commissioning and the data run.
Running and commissioning is very spread out in time, killing the SLAC travel budget | Delay on the commissioning and Data Runs | Close contact with Jlab to track the progress toward the HallB beamline contruction, to implement procativ action to save budget.

## Slide 28: Project Monitoring
Schedule Management Tracking of Schedule and Milestones
Financial Management Tracking WBS
Quality Management Consistency with Requirements (Reviews) Resource Management Manpower Leveling
Risk Management Risk Assessment and Mitigation
Procurement Management Purchase of Items > $15k
Monthly meetings, PM (Chair) + Prj.Sci.s + Subgroup Leaders

## Slide 29: PM Executive Summary
HPS has deployed :
Experienced Team for the construction
Clear Organization with a Project Management team
Detailed Schedule with reasonable float
Detailed Budget with contingencies
Manpower uploaded and leveled with explicit names
Risk Mitigation Plan

## Slide 30
Back Up SLIDES

## Slide 31: Beamline Costs: Upstream vs. Downstream
Beamline Downstream - ALCOVE | Labor | M&S | Total
Refurbishing of the Alcove | $202 | $118 | $320
Platform in the Alcove | $57 | $53 | $110
Magnet Power | $9 | $26 | $35
Beamline controls | $136 | $39 | $175
Beamline Upstream (Proposal) | Labor | M&S | Total
Items not required in the Alcove | $8 | $65 | $74
Vacuum beam line downstream of chicane | $0 | $19 | $19
Frascati Vacuum Chamber | $0 | $19 | $19
Photon Dump & Shielding | $8 | $27 | $35
Saving $74k =
Increase $320k -
With the recent CEBAF Re-Baselining Review, JLAB management has led the development of a realistic schedule for HPS in Hall B.
HPS can be installed in September, 2014, commissioned in early FY2015, and take data later in FY2015 if it is installed in the Hall B Downstream Alcove instead of the upstream location described in the proposal.
Alcove running is fully compatible with CLAS 12 assembly schedule in Hall B and ideal for future running when CLAS 12 is operational.
Net Incr. $246k
The additional costs to refurbish the Alcove are considered HPS Infrastructures

## Slide 32: SVT Project Budget
 | Labor (w/ cont.) | Material (w/ cont.) | Total (w/ cont.) | Capital Eq.
Layers 1-3 | $66K | $37K | $103K | $103K
Layers 4-6 | $107K | $86K | $193K | $175K
Support, Cooling, Vacuum | $143K | $20K | $163K | $107K
Testing, Shipping, Integration | $136K | $61K | $197K | $154K
Total | $452K | $204K | $656K | $539K
Biggest items are completely new modules for Layers 4-6 and testing/integration at SLAC.
SVT “upgrades” have been designed around scope we understand; scope of the Test SVT
Budget includes significant contingency beyond actual spending on similar items for Test SVT

## Slide 33: SVT DAQ - Budget
 | Labor w/ cont. | Material w/ cont. | Total | Capital Eq.
SVT DAQ | $431 | $352 | $782 | $540
FE Boards | $84 | $64 | $148 | $111
FE Interface Board | $10 | $0 | $10 | $0
Flange Board | $25 | $25 | $51 | $41
DAQ | $213 | $120 | $334 | $235
Hybrid | $48 | $26 | $74 | $65
Flex Cable | $41 | $13 | $54 | $54
PS & Cables | $0 | $70 | $70 | $0
HV/LV Cables | $9 | $33 | $42 | $34
Chart: 
| 41365 | 41395 | 41426 | 41456 | 41487 | 41518 | 41548 | 41579 | 41609 | 41640 | 41671
 | 0.024526 | 0.088237 | 0.047996 | 0.10722 | 0.054976 | 0.064188 | 0.38138 | 0.10221 | 0.032855 | 0.05933 | 0.037081
 | 0.024526 | 0.11276 | 0.16076 | 0.26798 | 0.32296 | 0.38715 | 0.76852 | 0.87073 | 0.90359 | 0.96292 | 1
RCE platform components and power supplies
Spending Profile in %

## Slide 34: ECAL Budget
Emphasis here on European contribution
  INFN committed to
    MB Design and construction
    LMS Design
    Crystal characterization tooling & manpower
  IPNO committed to
    All mechanic design and most construction
    Preamplifier design and production
    LMS construction
    Manpower for ECal assembly
Total 223 k€ (290 k$)
+ contingency 65k€
Does not include physicist/postdoc salaries

## Slide 35: Schedule and Budget –TDAQ
TDAQ ready Dec.6, 2013 (Integration in the existing TDAQ of the Hall-B)
 | Labor | Material | Total | Capital Eq.
TDAQ | $151 | $10 | $161 | $151
Update firmware on FADC250 | $21 | $0 | $21 | $21
New firmware for cluster finding | $50 | $0 | $50 | $50
New firmware for SSP | $37 | $0 | $37 | $37
Trigger monitoring tools | $43 | $0 | $43 | $43
Data Storage | $0 | $10 | $10 | $0
TDAQ Budget

## Slide 36: Schedule – Slow Control
Slow Control Starts July’13. Ready Aug.1, 2014
 | Labor w/ cont. | Material w/ cont. | Total | Capital Eq.
Slow Control | $94 | $39 | $134 | $106

## Slide 37: HPS DOE Review 7/11/13 : Charges
The quality and the impact of the research by the HPS collaboration in the recent past
The scientific significance, merit and feasibility of the proposal research;
The competence and future premise of the HPS collaboration for carrying out the proposed research;
The adequacy of the resources for carrying out the proposed research and cost-effectiveness of the research investment;
The quality of the support and the infrastructure provided by the participating laboratories.
Did the HPS collaboration successfully demonstrates the technical feasibility of its detector design in its 2012 test run at JLAB ?
Has the HPS collaboration developed technical design and construction and commissioning plans for its components that are consistent with the readiness to begin taking data in FY15 in the low energy beam in Hall B at JLAB ?
Has the HPS collaboration identified and costed for the appropriate manpower and the other resources consistent with readiness to take data in FY15 ?
Has the HPS collaboration presented estimates of cost and schedule that are consistent with readiness to take data in FY15
Has the HPS collaboration developed a credible staging plan installation of detector components that will allow for data taking in FY15 ?